## Done
12/02/20	Commscope	First implementation of the code generation started. Very simple kinematic vehicle model used here. No tire model used.	5
13/02/20	Group T	Improving the implementation of yesterday. Adding constraints on input and tweaking weights in the cost function.	5
14-17/02/20		Finally figured out how to set different constraints for the decision variables.	7
20-22/02/20		Swapping the simple kinematic model by a more complex dynamic one. Not working yet. The solver keeps giving an error. Might have to do with the parameters of tires being taken from the internet, while the car dimensions are actually real from FEB.	5
		Nope. That wasn’t the problem. Trying to fix a better cost function (till now it was just error ^2 from the reference).

## TODO
Working first implementation – cost function, constraints, model.	The output should make sense, i.e. if I want the reference to be [1,1,0,0], the final state should effectively get there.	23/02/20
FROM HERE ON (latest), IT WOULD BE NICE TO BE ABLE TO TEST STUFF ON THE TEST PLATFORM, WITH REAL DATA.
Improvement on the model – dynamic bicycle model + tire forces, constraints.		08/03/20
Improvement on the cost function – look into different errors that need to be taken into account.		15/03/20
Testing, tweaking values, weights on the cost function, etc.		22/03/20
Any more possible improvements?		29/03/20